## Goods Received
GOODS RECEIVED NOTE
What actually arrived, what was accepted, and the middle leg of the three-way match · complete at the gate, before the driver leaves
Buyer |  | Ashdown Groundworks Ltd |  |  | GRN number |  | GRN-0227
Supplier |  | Brackwell Aggregates Ltd |  |  | Date received |  | 04/01/2026
Project |  | Kingsmead Depot Refurbishment |  |  | Supplier delivery note no. |  | BA-118442
Site address |  | Kingsmead Depot, Northfield Road, Kingsmead KM4 7QT |  |  | Vehicle registration |  | YK71 HRV
Purchase order number |  | PO-2026-0418 |  |  | Driver name |  | M. Fenwick
[5 empty] | Checked by |  | R. Pardoe, Site Manager
PO line ref | Description | Quantity ordered | Quantity delivered | Quantity accepted | Quantity rejected | Reason for rejection or shortfall | Unit | Unit rate (£) | Value accepted (£) | Three-way match
1 | Type 1 granular sub-base, 40mm to dust | 60 | 60 | 58 |  | Two tonnes contaminated with clay, rejected at the gate | t | 24.5 |  | Query raised
2 | Concrete gully pot, 450mm diameter | 12 | 12 | 12 |  |  | nr | 38 |  | Matched
3 | Class HB2 kerb, 125 x 255mm, straight | 120 | 100 | 100 |  | Short delivery — balance to follow on the next load | m | 11.2 |  | Query raised
Goods Received — total
DELIVERY SUMMARY
Value accepted at this delivery |  |  |  |  | Total of the grid above
Value rejected or not delivered |  | 273 |  |  | Two tonnes of Type 1 and twenty metres of kerb
Supplier invoice value, excluding VAT |  | 3270 |  |  | From the invoice when it arrives
Difference to investigate |  |  |  |  | A credit note is due where the invoice exceeds what was accepted
CHECKS AT THE GATE
Quantity counted against the purchase order line, not just the order number. Condition inspected and damage recorded before the driver leaves. Material safety information received where the product requires it. The supplier’s delivery note signed only for what was actually accepted.
Party |  | Name (print) |  | Position |  | Signature |  | Date
Received and checked by
Delivered by (driver)

## Discrepancy Log
DISCREPANCY LOG
Every issue raised, its value, and whether it was ever closed
Buyer |  |  |  | GRN number
Supplier |  |  |  | Date received
Project |  |  |  | Supplier delivery note no.
Site address |  |  |  | Vehicle registration
Purchase order number |  |  |  | Driver name
Checked by
GRN no. | Date raised | Supplier | Issue | Detail | Value at risk (£) | Raised with | Credit note / resolution ref | Closed date | Status
GRN-0227 | 2026-01-04 | Brackwell Aggregates Ltd | Damaged | Two tonnes of Type 1 contaminated with clay, rejected at the gate | 49 | S. Ellery, Brackwell |  |  | Awaiting supplier
GRN-0227 | 2026-01-04 | Brackwell Aggregates Ltd | Short delivery | Twenty metres of HB2 kerb not delivered, balance promised next load | 224 | S. Ellery, Brackwell |  |  | Awaiting supplier
Discrepancy Log — total

## How to use
Goods received note — how to use this workbook
FIELD BY FIELD
A goods received note records what actually arrived on site: quantity, condition, and who checked it. It is the middle leg of the three-way match between the purchase order, the goods received note and the supplier invoice.
There is no statutory requirement to raise a goods received note. HMRC’s list of VAT records names orders, delivery notes and purchase invoices — not goods received notes. The GRN is a commercial control you keep because it is the only independent evidence of what turned up.
Quantity ordered, delivered and accepted are three different numbers, which is why they are three different columns. Copying the order quantity across is how short deliveries get paid for in full.
Reason for rejection: write it on the note and on the supplier’s delivery note before you sign theirs, and photograph anything you are rejecting. A rejection raised a week later is a credit note argument you will probably lose.
PO line ref: match to the line, not just the order number. Part-deliveries against a call-off order are the most common source of over-payment.
Quantities are not totalled. A column holding tonnes, metres and each has no meaningful sum, so only the value columns carry a total.
Three-way match status: the column the accounts team reads. A line left at "Not yet" when the invoice arrives is a line nobody has checked.
Keep the supplier’s delivery note with this one. Theirs is the supplier’s account of the delivery; this is yours, and the difference between them is where disputes are settled.
Discrepancy Log: one row per issue, with the value at risk and who it was raised with. A short delivery nobody logged becomes a credit note nobody chases.
SOURCES
HMRC, VAT Notice 700/21 "Keeping VAT records", section 2.3 — gov.uk/government/publications/vat-notice-70021-keeping-vat-records
AccountingTools, "Three-way matching" — accountingtools.com/articles/what-is-three-way-matching.html
This template is general information, not legal advice. Contract particulars routinely amend the default timings — always check your own contract.
Version 2.0 · Last reviewed 2 September 2026 · sitesamurai.co.uk/resources/construction-procurement