## Application
APPLICATION FOR PAYMENT No. 7
Payee’s notice under section 110A of the Housing Grants, Construction and Regeneration Act 1996 · complete the yellow cells only
Payer (employer / main contractor) | Northfield Civil Engineering Ltd |  | Contract form | JCT SBC/Q 2016
Payee (applicant) | Ashdown Groundworks Ltd |  | Valuation / assessment date | 2026-01-15
Project | Kingsmead Depot Refurbishment |  | Payment due date
Site address | Kingsmead Depot, Northfield Road, Kingsmead KM4 7QT |  | Payer's notice by
Contract reference | KMD/2025/014 |  | Pay less notice deadline
Application / valuation number | 7 |  | Final date for payment
|  |  | Claim date — Scheme only | 2026-01-15
VALUATION SUMMARY
Measured work valued to date |  |  | Measured Work sheet
Variations agreed |  |  | Variations sheet
Dayworks agreed |  |  | Dayworks sheet
Materials on site |  |  | Materials on Site sheet
Preliminaries |  |  | Preliminaries sheet
Gross valuation to date, excluding VAT |  |  | Sum of the five sections above
Retention percentage |  | 3% | From the contract particulars. JCT default 3%, commonly amended to 5%.
Less: retention held |  |  | Gross valuation multiplied by the retention percentage
Less: previously certified |  | 80000 | Total certified on earlier valuations, excluding VAT
Net amount applied for, excluding VAT |  |  | The notified sum unless a compliant payer notice states otherwise
VAT treatment |  | Standard rate 20% | Reverse charge applies to most CIS-reportable supplies between VAT-registered businesses
VAT |  |  | Zero on a reverse-charge supply — state that on the invoice instead
Total now applied for, including VAT |  |  | Carry this figure to the invoice
NOTIFIED SUM AND BASIS OF CALCULATION
This application states the sum the payee considers to be due at the payment due date and the basis on which that sum is calculated, as section 110A of the Housing Grants, Construction and Regeneration Act 1996 requires of a payee’s notice.
If the payer gives no compliant payment notice by the date shown above and no valid pay less notice by the pay less deadline, the net amount applied for becomes the notified sum and is payable in full by the final date for payment.
The basis of calculation is the five detail sheets in this workbook. Every line carries a bill item, an instruction reference, a signed daywork sheet number or a delivery record, so the payer can check it without rebuilding the valuation.
Retention is a contractual deduction, not a set-off, and does not require a pay less notice. Any other deduction does.
Party | Name (print) | Position | Signature | Date
Payee (applicant)
Payer (received by)

## Measured Work
MEASURED WORK
Bill items and schedule lines valued at the valuation date
Payer (employer / main contractor) |  |  |  |  | Contract form
Payee (applicant) |  |  |  |  | Valuation / assessment date
Project |  |  |  |  | Payment due date
Site address |  |  |  |  | Payer's notice by
Contract reference |  |  |  |  | Pay less notice deadline
Application / valuation number |  |  |  |  | Final date for payment
Item / bill ref | Description of works | Contract sum for item (£) | % complete at this date | Gross value to date (£) | Previously applied (£) | Value this period (£)
A/1 | Site clearance, setting out and temporary fencing | 8200 | 100% |  | 8200
A/2 | Excavation and disposal off site to licensed tip | 22000 | 100% |  | 20000
B/1 | Mass fill foundations and reinforced ground beams | 26000 | 100% |  | 22000
B/2 | Foul and surface water drainage including manholes | 20000 | 90% |  | 14000
C/1 | Type 1 sub-base and precast kerbing to service yard | 12000 | 75% |  | 6000
C/2 | Perimeter fencing, gates and bollards | 7000 | 60% |  | 2000
Measured Work — total

## Variations
VARIATIONS
Instructed changes, agreed and carried into this valuation
Payer (employer / main contractor) |  |  |  | Contract form
Payee (applicant) |  |  |  | Valuation / assessment date
Project |  |  |  | Payment due date
Site address |  |  |  | Payer's notice by
Contract reference |  |  |  | Pay less notice deadline
Application / valuation number |  |  |  | Final date for payment
Variation no. | Instruction ref | Date instructed | Description of the change | Status | Value (£) | Previously applied (£) | Value this period (£)
VO-004 | AI-017 | 2025-11-22 | Additional 150mm capping layer to service yard following CBR results | Agreed | 7250 | 0
VO-005 | AI-021 | 2025-12-04 | Relocate foul manhole MH3 clear of incoming statutory services | Agreed | 3400 | 0
VO-006 | AI-023 | 2026-01-09 | Additional road gully and connection at service yard low point | Agreed | 1850 | 0
Variations — total
Agreed, carry to the application — total
Quoted, awaiting agreement — total
Notified, not yet quoted — total
Disputed or rejected — total

## Dayworks
DAYWORKS
Signed daywork sheets priced per the RICS Definition of Prime Cost of Daywork
Payer (employer / main contractor) |  |  |  | Contract form
Payee (applicant) |  |  |  | Valuation / assessment date
Project |  |  |  | Payment due date
Site address |  |  |  | Payer's notice by
Contract reference |  |  |  | Pay less notice deadline
Application / valuation number |  |  |  | Final date for payment
Sheet no. | Date of works | Instruction ref | Description of work | Signed on site by | Labour (£) | Plant (£) | Materials (£) | % addition | Sheet total (£)
DW-011 | 2025-12-08 | AI-019 | Break out unrecorded mass concrete obstruction at MH2 | R. Pardoe, Site Manager | 1240 | 460 | 0 | 12.5%
DW-012 | 2026-01-06 | AI-022 | Standing time — no yard access during third-party crane lift | R. Pardoe, Site Manager | 940 | 0 | 248.89 | 12.5%
Dayworks — total

## Materials on Site
MATERIALS ON SITE
Unfixed materials, claimable only where the contract allows it
Payer (employer / main contractor) |  |  |  | Contract form
Payee (applicant) |  |  |  | Valuation / assessment date
Project |  |  |  | Payment due date
Site address |  |  |  | Payer's notice by
Contract reference |  |  |  | Pay less notice deadline
Application / valuation number |  |  |  | Final date for payment
Item | Description | Supplier | Delivery note ref | Invoice ref | Value on site (£) | Vested and insured | Previously applied (£) | Value this period (£)
M/1 | Class HB2 precast kerb, 125 x 255mm, stockpiled in the compound | Brackwell Aggregates Ltd | BA-118442 | BA-INV-20441 | 2600 | Yes | 0
M/2 | Type 1 granular sub-base, 65t stockpiled to the service yard | Brackwell Aggregates Ltd | BA-118501 | BA-INV-20488 | 1600 | Yes | 0
Materials on Site — total

## Preliminaries
PRELIMINARIES
Time-related, fixed and value-related preliminaries earned to date
Payer (employer / main contractor) |  |  |  | Contract form
Payee (applicant) |  |  |  | Valuation / assessment date
Project |  |  |  | Payment due date
Site address |  |  |  | Payer's notice by
Contract reference |  |  |  | Pay less notice deadline
Application / valuation number |  |  |  | Final date for payment
Item | Description | Basis | Contract sum (£) | % complete | Value to date (£) | Previously applied (£) | Value this period (£)
P/1 | Site welfare, cabins and temporary services | Time-related | 5000 | 70% |  | 3200
P/2 | Site supervision and setting out | Time-related | 4500 | 70% |  | 2900
P/3 | Plant standing and small tools allowance | Time-related | 2500 | 70% |  | 1700
Preliminaries — total

## How to use
Application for payment — how to use this workbook
FIELD BY FIELD
Payer and payee: the two parties to this contract. On a subcontract the payer is the main contractor, not the employer at the top of the chain.
Contract form: pick the form your contract is written on. The four dates below it are calculated from the day counts that form uses, and they flow through to every other sheet in the workbook.
Valuation / assessment date: the Interim Valuation Date under JCT, the assessment date under NEC4, or the end of the relevant period under the Scheme. Value what was built at that date, not at the date you do the paperwork.
Measured Work: one row per bill item or schedule line. Enter the contract sum and the percentage complete; the gross value to date is calculated. The previously applied column is per item, so an argument about one item does not require the whole valuation to be reconstructed.
Variations: only variations that have been instructed and agreed belong here. Log the instruction reference on every row — a variation with no instruction usually has no contractual route to payment.
Dayworks: enter the labour, plant and materials from the signed sheet and the percentage addition your contract allows. Show the addition as its own column so the payer can check it against the contract rather than take it on trust.
Materials on site: only claimable where the contract allows it, and usually only where the materials are properly stored, insured and identified as yours. The vested and insured column is there to be answered before the claim is made.
Preliminaries: time-related preliminaries are earned by elapsed time, fixed preliminaries on the event they relate to. Applying for the whole preliminaries sum on a percentage of measured value is the most common preliminaries error.
Retention percentage: from the contract particulars. The JCT default is 3%, very commonly amended upward to 5%. There is no statutory retention scheme, so the contract is the only authority for the number.
Less previously certified: the total certified on earlier valuations, excluding VAT. Take it from the certificates, not from your own earlier applications — the difference between the two is exactly what this column is for.
VAT treatment: most CIS-reportable supplies between VAT-registered businesses fall under the domestic reverse charge, where the customer accounts for the VAT and this application shows none.
Submit the application on the day it is due and diarise the payer’s notice date the workbook has calculated. A payer who lets that date pass without a compliant notice owes the net amount applied for.
STATUTORY AND STANDARD-FORM TIMINGS
Day counts are calendar days. The workbook computes the four dates in the header from the contract form you pick and the valuation date you enter.
Contract form | Due date | Payer's notice | Final date | Pay less by
JCT SBC/Q 2016 — JCT Standard Building Contract with Quantities 2016 (SBC/Q) | +7 days | +5 days | +14 days | -5 days
JCT DB 2016 — JCT Design and Build 2016 (DB) | +7 days | +5 days | +14 days | -5 days
NEC4 ECC — NEC4 Engineering and Construction Contract | +7 days | +0 days | +14 days | -7 days
Scheme default — Scheme for Construction Contracts (default) | +7 days | +5 days | +17 days | -7 days
Due date counts from the valuation, assessment or period-end date. The payer’s notice and the final date count from the due date. The pay less deadline counts back from the final date.
SOURCES
Housing Grants, Construction and Regeneration Act 1996, Part II, ss.109–111 (as amended by the Local Democracy, Economic Development and Construction Act 2009) — legislation.gov.uk/ukpga/1996/53/part/II
Scheme for Construction Contracts (England and Wales) Regulations 1998, Schedule Part II, paragraphs 4, 8, 9 and 10 — legislation.gov.uk/uksi/1998/649/schedule/part/II
JCT, "JCT explains: interim payments" (SBC/Q 2016 clauses 4.9 and 4.11) — corporate.jctltd.co.uk/jct-explains-interim-payments/
NEC4 ECC clauses 50.1, 51.1 and 51.2 and secondary Option Y(UK)2, as summarised by HKA, "How to get your NEC4 ECC pay less notice right under Y(UK)2" — hka.com
This template is general information, not legal advice. Contract particulars routinely amend the default timings — always check your own contract.
Version 2.0 · Last reviewed 2 September 2026 · sitesamurai.co.uk/resources/get-paid-on-time