DAYWORK SHEET

Prime cost of daywork

Complete on site, on the day the work is done, and get it signed before anyone leaves. A sheet signed a fortnight later is the sheet most likely to be refused at valuation.

| Reference | DW-011 |
| --- | --- |
| Date | 08/12/2025 |
| Version | Worked example |

## 1. SHEET DETAILS

| Daywork sheet number | DW-011 |
| --- | --- |
| Project | Kingsmead Depot Refurbishment |
| Contract reference | KMD/2025/014 |
| Date of works | 08/12/2025 |
| Location on site | Manhole MH2, service yard |
| Weather | Dry, 4°C |
| Instruction reference | AI-019 |
| Instructed by (name and position) | H. Okafor, Quantity Surveyor |

## 2. DESCRIPTION OF WORK

Say what was done and why it could not be measured and valued under the contract rates.

| Description of work carried out | Reason daywork applies |
| --- | --- |
| Break out unrecorded mass concrete obstruction at manhole MH2 and dispose off site | Obstruction not shown on the survey or the bill; no contract rate covers breaking out mass concrete |

## 3. LABOUR

| Name | Trade or grade | Start | Finish | Hours | Rate (£/hr) | Total (£) |
| --- | --- | --- | --- | --- | --- | --- |
| J. Mbeki | Ganger | 07:30 | 15:30 | 8.00 | 36.00 | 288.00 |
| T. Reilly | Operative | 07:30 | 15:30 | 8.00 | 28.00 | 224.00 |
| S. Kaur | Operative | 07:30 | 15:30 | 8.00 | 28.00 | 224.00 |
| A. Novak | Machine driver | 07:30 | 15:30 | 8.00 | 32.00 | 256.00 |
| P. Dalton | Banksman | 07:30 | 15:30 | 8.00 | 31.00 | 248.00 |

## 4. PLANT AND EQUIPMENT

| Plant or equipment | Owned or hired | Hours or days | Rate (£) | Total (£) |
| --- | --- | --- | --- | --- |
| 8 tonne tracked excavator | Hired | 8.00 | 42.50 | 340.00 |
| Hydraulic breaker attachment | Hired | 8.00 | 15.00 | 120.00 |

## 5. MATERIALS

| Material and supplier | Delivery or invoice ref | Quantity | Unit rate (£) | Total (£) |
| --- | --- | --- | --- | --- |
| None on this sheet | — | — | — | 0.00 |

## 6. TOTALS

Show each prime cost, the percentage addition the contract allows, and the total it produces. A single total over a table that adds to something else is the line a payer refuses.

| Labour prime cost (£) | £1,240.00 |
| --- | --- |
| Labour percentage addition at 12.5% (£) | £155.00 |
| Labour total (£) | £1,395.00 |
| Plant prime cost (£) | £460.00 |
| Plant percentage addition at 12.5% (£) | £57.50 |
| Plant total (£) | £517.50 |
| Materials prime cost (£) | £0.00 |
| Materials percentage addition at 12.5% (£) | £0.00 |
| Materials total (£) | £0.00 |
| Sheet total, excluding VAT (£) | £1,912.50 |

## 7. SITE SIGNATURE

Signature below confirms the resources and hours recorded on this sheet. It is not an agreement that the work is a daywork, nor an agreement of the rates or the total, unless stated otherwise in writing.

Signed on site by (name and position):  R. Pardoe, Site Manager

Company:  Northfield Civil Engineering Ltd

Date:  08/12/2025

| Party | Name (print) | Position | Signature | Date |
| --- | --- | --- | --- | --- |
| Payee’s representative | D. Whitcombe | Contracts Manager |  | 08/12/2025 |
| Payer’s representative | R. Pardoe | Site Manager |  | 08/12/2025 |

## 8. SUBMISSION

- Submit the signed sheet with the next payment application and record which valuation it was included in.

- Dayworks carried out with no instruction usually have no contractual route to payment, whatever the sheet says.

- Percentage additions for overhead and profit are contractual and vary. Show them as a separate line so the payer can check them.

## SOURCES

Housing Grants, Construction and Regeneration Act 1996, Part II, ss.109–111 (as amended by the Local Democracy, Economic Development and Construction Act 2009) — legislation.gov.uk/ukpga/1996/53/part/II

JCT, "JCT explains: interim payments" (SBC/Q 2016 clauses 4.9 and 4.11) — corporate.jctltd.co.uk/jct-explains-interim-payments/

This template is general information, not legal advice. Contract particulars routinely amend the default timings — always check your own contract.

Version 2.0 · Last reviewed 2 September 2026