SITE SAMURAI	Prime cost of daywork
DAYWORK SHEET
Prime cost of daywork
Complete on site, on the day the work is done, and get it signed before anyone leaves. A sheet signed a fortnight later is the sheet most likely to be refused at valuation.
	Reference
	DW-011

	Date
	08/12/2025

	Version
	Worked example


1. SHEET DETAILS
	Daywork sheet number
	DW-011

	Project
	Kingsmead Depot Refurbishment

	Contract reference
	KMD/2025/014

	Date of works
	08/12/2025

	Location on site
	Manhole MH2, service yard

	Weather
	Dry, 4°C

	Instruction reference
	AI-019

	Instructed by (name and position)
	H. Okafor, Quantity Surveyor


2. DESCRIPTION OF WORK
Say what was done and why it could not be measured and valued under the contract rates.
	Description of work carried out
	Reason daywork applies

	Break out unrecorded mass concrete obstruction at manhole MH2 and dispose off site
	Obstruction not shown on the survey or the bill; no contract rate covers breaking out mass concrete


3. LABOUR
	Name
	Trade or grade
	Start
	Finish
	Hours
	Rate (£/hr)
	Total (£)

	J. Mbeki
	Ganger
	07:30
	15:30
	8.00
	36.00
	288.00

	T. Reilly
	Operative
	07:30
	15:30
	8.00
	28.00
	224.00

	S. Kaur
	Operative
	07:30
	15:30
	8.00
	28.00
	224.00

	A. Novak
	Machine driver
	07:30
	15:30
	8.00
	32.00
	256.00

	P. Dalton
	Banksman
	07:30
	15:30
	8.00
	31.00
	248.00


4. PLANT AND EQUIPMENT
	Plant or equipment
	Owned or hired
	Hours or days
	Rate (£)
	Total (£)

	8 tonne tracked excavator
	Hired
	8.00
	42.50
	340.00

	Hydraulic breaker attachment
	Hired
	8.00
	15.00
	120.00


5. MATERIALS
	Material and supplier
	Delivery or invoice ref
	Quantity
	Unit rate (£)
	Total (£)

	None on this sheet
	—
	—
	—
	0.00


6. TOTALS
Show each prime cost, the percentage addition the contract allows, and the total it produces. A single total over a table that adds to something else is the line a payer refuses.
	Labour prime cost (£)
	£1,240.00

	Labour percentage addition at 12.5% (£)
	£155.00

	Labour total (£)
	£1,395.00

	Plant prime cost (£)
	£460.00

	Plant percentage addition at 12.5% (£)
	£57.50

	Plant total (£)
	£517.50

	Materials prime cost (£)
	£0.00

	Materials percentage addition at 12.5% (£)
	£0.00

	Materials total (£)
	£0.00

	Sheet total, excluding VAT (£)
	£1,912.50


7. SITE SIGNATURE
Signature below confirms the resources and hours recorded on this sheet. It is not an agreement that the work is a daywork, nor an agreement of the rates or the total, unless stated otherwise in writing.
Signed on site by (name and position):  R. Pardoe, Site Manager
Company:  Northfield Civil Engineering Ltd
Date:  08/12/2025
	Party
	Name (print)
	Position
	Signature
	Date

	Payee’s representative
	D. Whitcombe
	Contracts Manager
	 
	08/12/2025

	Payer’s representative
	R. Pardoe
	Site Manager
	 
	08/12/2025


8. SUBMISSION
1. Submit the signed sheet with the next payment application and record which valuation it was included in.
1. Dayworks carried out with no instruction usually have no contractual route to payment, whatever the sheet says.
1. Percentage additions for overhead and profit are contractual and vary. Show them as a separate line so the payer can check them.
SOURCES
Housing Grants, Construction and Regeneration Act 1996, Part II, ss.109–111 (as amended by the Local Democracy, Economic Development and Construction Act 2009) — legislation.gov.uk/ukpga/1996/53/part/II
JCT, "JCT explains: interim payments" (SBC/Q 2016 clauses 4.9 and 4.11) — corporate.jctltd.co.uk/jct-explains-interim-payments/
This template is general information, not legal advice. Contract particulars routinely amend the default timings — always check your own contract.
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