## Final Account
FINAL ACCOUNT STATEMENT
From the original contract sum to the final balance, line by line, with the evidence for each · complete the yellow cells only
Payer (employer / main contractor) |  | Northfield Civil Engineering Ltd | Contract form |  | JCT SBC/Q 2016
Payee |  | Ashdown Groundworks Ltd | Valuation / assessment date |  | 2026-01-15
Project |  | Kingsmead Depot Refurbishment | Payment due date
Site address |  | Kingsmead Depot, Northfield Road, Kingsmead KM4 7QT | Payer's notice by
Contract reference |  | KMD/2025/014 | Pay less notice deadline
Final date for payment
|  |  | Claim date — Scheme only |  | 2026-01-15
Line ref | Element | Description | Supporting reference | Claimed (£) | Agreed (£) | Difference (£) | Status | Notes
1 | Original contract sum | Groundworks, drainage and external works package | Subcontract order KMD/2025/014 | 109500 | 109500 |  | Agreed
2 | Measured works remeasure | Drainage remeasure — additional 62m of 225mm pipe | Remeasure sheet RM-03 | 4600 | 4100 |  | Agreed | Settled at 4,100
3 | Variation | VO-002 and VO-003, agreed at valuation 6 | Variation Register | 4100 | 4100 |  | Agreed
4 | Variation | VO-004 to VO-006, agreed at valuation 7 | Variation Register | 12500 | 12500 |  | Agreed
5 | Variation | VO-001 omission — precast headwall | AI-004 | -2600 | -2600 |  | Agreed
6 | Daywork | DW-011 and DW-012, signed on site | Daywork sheets | 3250 | 3250 |  | Agreed
7 | Contra charge | Cleaning of adopted highway after silt run-off | Contra note CN-02 | -450 | -450 |  | Agreed
8 | Loss and expense | Prolongation for the third-party crane possession | Claim submission LE-01 | 3800 | 0 |  | Disputed | Open at the date of this statement
Final Account — total
FINAL ACCOUNT SUMMARY
Original contract sum |  | 109500
Add: measured works remeasure |  | 4100
Add: variations agreed |  | 16600 | VO-002 to VO-006
Less: omissions |  | -2600
Add: dayworks agreed |  | 3250
Add: loss and expense agreed |  | 0 | LE-01 still disputed
Final contract sum, excluding VAT
Less: contra charges |  | -450
Less: liquidated damages |  | 0
Adjusted final sum
Less: retention still held |  | 1956 | Second moiety, released on the certificate of making good
Less: previously certified |  | 112277.5 | Total of the payment schedule
Final balance now due, excluding VAT
STATEMENT
This statement sets out the sum the party issuing it considers to be the final sum under the contract and the basis of that calculation. Lines marked disputed are not agreed and are not withdrawn by the issue of this statement.
Party | Name (print) | Position | Signature | Date
Issued by
Agreed by

## Close-out Checklist
CLOSE-OUT CHECKLIST
The documents the account cannot be agreed without
Payer (employer / main contractor) |  |  | Contract form
Payee |  |  | Valuation / assessment date
Project |  |  | Payment due date
Site address |  |  | Payer's notice by
Contract reference |  |  | Pay less notice deadline
Final date for payment
Claim date — Scheme only
Item | Owner | Target date | Completed date | Evidence reference | Status | Notes
As-built drawings issued and accepted
Operation and maintenance manuals issued
Test and commissioning certificates issued
CCTV drainage survey and adoption paperwork
Health and safety file information handed over
Statutory approvals and sign-offs closed out
Defects list agreed and cleared
Certificate of making good issued
All variations instructed in writing and priced
All daywork sheets signed and submitted
Final account submitted with supporting evidence
Retention release requested

## How to use
Final account statement — how to use this workbook
FIELD BY FIELD
The final account is the arithmetic that takes the original contract sum to the final sum: remeasure, variations, compensation events, dayworks, provisional sums, loss and expense, and any deduction the payer is entitled to.
Claimed and agreed sit side by side. A statement showing only the agreed column hides the gap you are negotiating; one showing only the claimed column tells the payer nothing about where you have already moved.
Supporting reference: a final account is settled on the strength of instructions, signed daywork sheets, measured records and correspondence, not on the total. Every line needs one.
Status: leave a disputed line disputed. Rolling an open claim into the agreed column to make the total look tidier is how the claim gets lost.
The final account is still a payment under the contract. When the final sum is certified it goes through the same payment notice and pay less notice machinery as every interim payment, on the dates in the header.
Retention is dealt with separately. It is released on its own contractual trigger dates, not as part of agreeing the final sum, so the statement deducts only the retention still held.
Close-out Checklist: the documents that have to exist before the account can be agreed. An account held up by a missing O&M manual is held up just as long as one held up by money.
If the account is agreed and then not paid, statutory interest runs at 8% above the Bank of England base rate, plus fixed compensation of £40, £70 or £100 depending on the size of the debt.
STATUTORY AND STANDARD-FORM TIMINGS
Day counts are calendar days. The workbook computes the four dates in the header from the contract form you pick and the valuation date you enter.
Contract form | Due date | Payer's notice | Final date | Pay less by
JCT SBC/Q 2016 — JCT Standard Building Contract with Quantities 2016 (SBC/Q) | +7 days | +5 days | +14 days | -5 days
JCT DB 2016 — JCT Design and Build 2016 (DB) | +7 days | +5 days | +14 days | -5 days
NEC4 ECC — NEC4 Engineering and Construction Contract | +7 days | +0 days | +14 days | -7 days
Scheme default — Scheme for Construction Contracts (default) | +7 days | +5 days | +17 days | -7 days
Due date counts from the valuation, assessment or period-end date. The payer’s notice and the final date count from the due date. The pay less deadline counts back from the final date.
SOURCES
Housing Grants, Construction and Regeneration Act 1996, Part II, ss.109–111 (as amended by the Local Democracy, Economic Development and Construction Act 2009) — legislation.gov.uk/ukpga/1996/53/part/II
Scheme for Construction Contracts (England and Wales) Regulations 1998, Schedule Part II, paragraphs 4, 8, 9 and 10 — legislation.gov.uk/uksi/1998/649/schedule/part/II
JCT, "JCT explains: interim payments" (SBC/Q 2016 clauses 4.9 and 4.11) — corporate.jctltd.co.uk/jct-explains-interim-payments/
Late Payment of Commercial Debts (Interest) Act 1998, s.5A, and gov.uk "Late commercial payments: charging interest and debt recovery" — legislation.gov.uk/ukpga/1998/20/section/5A
This template is general information, not legal advice. Contract particulars routinely amend the default timings — always check your own contract.
Version 2.0 · Last reviewed 2 September 2026 · sitesamurai.co.uk/resources/get-paid-on-time