## Valuation
INTERIM VALUATION No. ____
Measurement of the works at the valuation date · the arithmetic behind the payment application, not the application itself
Payer (employer / main contractor) |  |  |  |  | Contract form | JCT SBC/Q 2016
Payee |  |  |  |  | Valuation / assessment date
Project |  |  |  |  | Payment due date
Site address |  |  |  |  | Payer's notice by
Contract reference |  |  |  |  | Pay less notice deadline
Application / valuation number |  |  |  |  | Final date for payment
Claim date — Scheme only
Item / bill ref | Description of works | Contract sum for item (£) | % complete at this date | Gross value to date (£) | Previously applied (£) | Value this period (£)
Valuation — total
VALUATION SUMMARY
Measured work valued to date |  |  |  |  | Total of the grid above
Add: variations agreed |  |  |  |  | Instructed and agreed only
Add: dayworks agreed |  |  |  |  | Signed sheets only
Add: materials on site |  |  |  |  | Only where the contract allows it
Add: preliminaries |  |  |  |  | Time-related and fixed preliminaries earned to date
Gross valuation to date, excluding VAT
Retention percentage |  |  |  |  | From the contract particulars
Less: retention held
Less: previously certified |  |  |  |  | From the certificates
Net valuation, excluding VAT
Difference against the payee’s application |  |  |  |  | Enter the sum applied for
Shortfall or overpayment
CERTIFICATION
This valuation states the sum the valuer considers due at the valuation date and the basis of that calculation. Issued as, or attached to, a payment notice under section 110A of the Housing Grants, Construction and Regeneration Act 1996, the sum shown becomes the notified sum.
A valuation below the payee’s application is not by itself a pay less notice. To withhold against a notified sum the payer must give a pay less notice by the deadline in the header, stating the sum considered due and the basis of it.
Party | Name (print) | Position | Signature | Date
Valued by
Agreed by (payee)

## Valuation Record
VALUATION RECORD
What was valued and what was certified, cycle by cycle
Payer (employer / main contractor) |  |  |  | Contract form
Payee |  |  |  | Valuation / assessment date
Project |  |  |  | Payment due date
Site address |  |  |  | Payer's notice by
Contract reference |  |  |  | Pay less notice deadline
Application / valuation number |  |  |  | Final date for payment
Claim date — Scheme only
Valuation no. | Interim Valuation Date | Gross valued (£) | Certified (£) | Difference (£) | Reason for difference
Valuation Record — total

## How to use
Interim valuation — how to use this workbook
FIELD BY FIELD
An interim valuation measures what has actually been built at a fixed date. Value at the Interim Valuation Date, not at the date you happen to do the paperwork.
Contract form and valuation date: the four dates in the header are calculated from them. They are the dates the certificate, the payment notice and the payment itself have to hit.
Contract sum for item and % complete: the gross value to date is calculated from the two. Measuring by percentage is fine for a lump-sum item and wrong for a remeasurable one — remeasure those and enter the value directly against a 100% line.
Previously applied: per item, so a disagreement about one item does not require the whole valuation to be rebuilt.
Variations, dayworks and materials on site are valued separately from measured work in the summary, so a dispute about one does not hold up payment for the other.
Materials on site are usually only valuable where the contract says they are, and often only where they are properly stored, insured and identified. Check the contract before including them.
Difference against the payee’s application: the gap you are certifying. A month-by-month record of that gap is the evidence you need when an underpayment turns into an argument at final account.
Valuation Record: one row per cycle across the contract, with what was valued and what was certified. Fill it in as you go; reconstructing it at final account is far harder than keeping it.
STATUTORY AND STANDARD-FORM TIMINGS
Day counts are calendar days. The workbook computes the four dates in the header from the contract form you pick and the valuation date you enter.
Contract form | Due date | Payer's notice | Final date | Pay less by
JCT SBC/Q 2016 — JCT Standard Building Contract with Quantities 2016 (SBC/Q) | +7 days | +5 days | +14 days | -5 days
JCT DB 2016 — JCT Design and Build 2016 (DB) | +7 days | +5 days | +14 days | -5 days
NEC4 ECC — NEC4 Engineering and Construction Contract | +7 days | +0 days | +14 days | -7 days
Scheme default — Scheme for Construction Contracts (default) | +7 days | +5 days | +17 days | -7 days
Due date counts from the valuation, assessment or period-end date. The payer’s notice and the final date count from the due date. The pay less deadline counts back from the final date.
SOURCES
Housing Grants, Construction and Regeneration Act 1996, Part II, ss.109–111 (as amended by the Local Democracy, Economic Development and Construction Act 2009) — legislation.gov.uk/ukpga/1996/53/part/II
Scheme for Construction Contracts (England and Wales) Regulations 1998, Schedule Part II, paragraphs 4, 8, 9 and 10 — legislation.gov.uk/uksi/1998/649/schedule/part/II
JCT, "JCT explains: interim payments" (SBC/Q 2016 clauses 4.9 and 4.11) — corporate.jctltd.co.uk/jct-explains-interim-payments/
This template is general information, not legal advice. Contract particulars routinely amend the default timings — always check your own contract.
Version 2.0 · Last reviewed 2 September 2026 · sitesamurai.co.uk/resources/get-paid-on-time