SITE SAMURAI	JCT DB 2016
PAYMENT NOTICE
JCT DB 2016
Issued under JCT Design and Build Contract 2016 (DB). A notice under section 110A of the Housing Grants, Construction and Regeneration Act 1996.
	Reference
	PN-7 / KMD/2025/014

	Date
	27/01/2026

	Version
	Worked example


1. CONTRACT AND PAYMENT CYCLE
	Project
	Kingsmead Depot Refurbishment

	Contract reference
	KMD/2025/014

	Payer (issuing this notice)
	Northfield Civil Engineering Ltd

	Payee
	Ashdown Groundworks Ltd

	Payment cycle / valuation number
	7

	Interim valuation or assessment date
	15/01/2026

	Payment due date
	22/01/2026

	Final date for payment
	05/02/2026


2. NOTICE DETAILS
	Application or assessment being responded to
	Application 7, submitted 15/01/2026

	Sum applied for, excluding VAT
	£32,277.50

	Sum the payer considers due at the payment due date, excluding VAT
	£32,277.50

	VAT at 20%
	£6,455.50

	Total payable, including VAT
	£38,733.00

	Date of this notice
	27/01/2026


3. BASIS OF CALCULATION
	Element
	Description and reference
	Amount (£)

	Measured work
	Valuation 7, measured work sheet
	£87,400.00

	Variations
	VO-004 to VO-006, agreed and instructed
	£12,500.00

	Dayworks
	DW-011 and DW-012, signed on site
	£3,250.00

	Materials on site
	Kerb and sub-base stock, vested and insured
	£4,200.00

	Preliminaries
	Welfare, supervision and plant standing earned to date
	£8,400.00

	Gross valuation to date
	Sum of the five lines above
	£115,750.00

	Less: retention at 3%
	Contract particulars
	-£3,472.50

	Less: previously certified
	Valuations 1 to 6
	-£80,000.00

	Sum considered due, excluding VAT
	Net of retention and earlier certificates
	£32,277.50

	VAT at 20%
	Standard rate — no domestic reverse charge on this supply
	£6,455.50

	Total payable, including VAT
	The figure to pay by the final date
	£38,733.00


4. ISSUE AND SERVICE
Issued by (name and position):  H. Okafor, Quantity Surveyor
Method of service:  Email, as the contract particulars require
Date and time served:  27/01/2026 at 10:14
5. SIGN-OFF
	Party
	Name (print)
	Position
	Signature
	Date

	Payer
	H. Okafor
	Quantity Surveyor
	 
	27/01/2026




6. HOW TO USE THIS NOTICE
Reference, not part of the notice itself.
1. This notice must state the sum the payer considers to be or to have been due at the payment due date, and the basis on which that sum is calculated. A notice that states a figure without a basis is at risk of being held invalid.
1. Set out the basis line by line. Each one should be capable of being checked against a valuation, an instruction, a signed record or an invoice.
1. Serve the notice by the method the contract requires and keep proof of the date it was sent and received. The burden of showing a notice was served in time falls on the party who gave it.
1. A payment notice given late is not a payment notice. Where the payer gives none in time, the payee’s application becomes the notified sum and is payable in full by the final date for payment unless a valid pay less notice follows.
1. Retention deducted under the contract is not a set-off and needs no pay less notice. Any other deduction does, so keep the two apart on the basis of calculation.
1. The Contractor submits an Interim Application before the Interim Valuation Date, and that application drives the valuation.
1. The payment due date is 7 days after the Interim Valuation Date.
1. The Employer’s Payment Notice is given not later than 5 days after the due date.
1. The final date for payment is 14 days after the due date.
1. A Pay Less Notice must be given not later than 5 days before the final date for payment.
1. Where no Payment Notice is given, the Interim Application operates as the payment notice and its sum becomes the notified sum.
SOURCES
Gowling WLG, "JCT Design and Build 2016 — Interim Valuation Dates: what you need to know" (due date 7 days after the Interim Valuation Date, or 7 days after receipt of a late Interim Application; final date 14 days from the due date; pay less notice not later than 5 days before the final date) — gowlingwlg.com/en/insights-resources/articles/2016/jct-design-and-build-2016-interim-valuation-dates
Housing Grants, Construction and Regeneration Act 1996, Part II, ss.109–111 (as amended by the Local Democracy, Economic Development and Construction Act 2009) — legislation.gov.uk/ukpga/1996/53/part/II
This template is general information, not legal advice. Contract particulars routinely amend the default timings — always check your own contract.
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