PAYMENT NOTICE

NEC4 ECC

Issued under NEC4 Engineering and Construction Contract, with secondary Option Y(UK)2. A notice under section 110A of the Housing Grants, Construction and Regeneration Act 1996.

| Reference | [ … ] |
| --- | --- |
| Date | [ … ] |
| Version | 2.0 · reviewed 2 September 2026 |

## 1. CONTRACT AND PAYMENT CYCLE

| Project | [ … ] |
| --- | --- |
| Contract reference | [ … ] |
| Payer (issuing this notice) | [ … ] |
| Payee | [ … ] |
| Payment cycle / valuation number | [ … ] |
| Interim valuation or assessment date | [ … ] |
| Payment due date | [ … ] |
| Final date for payment | [ … ] |

## 2. NOTICE DETAILS

| Application or assessment being responded to | [ … ] |
| --- | --- |
| Sum applied for, excluding VAT | [ … ] |
| Sum the payer considers due at the payment due date, excluding VAT | [ … ] |
| VAT at 20% | [ … ] |
| Total payable, including VAT | [ … ] |
| Date of this notice | [ … ] |

## 3. BASIS OF CALCULATION

| Element | Description and reference | Amount (£) |
| --- | --- | --- |

## 4. ISSUE AND SERVICE

Issued by (name and position):  [ … ]

Method of service:  [ … ]

Date and time served:  [ … ]

## 5. SIGN-OFF

| Party | Name (print) | Position | Signature | Date |
| --- | --- | --- | --- | --- |
| Payer |  |  |  |  |

## 6. HOW TO USE THIS NOTICE

Reference, not part of the notice itself.

- This notice must state the sum the payer considers to be or to have been due at the payment due date, and the basis on which that sum is calculated. A notice that states a figure without a basis is at risk of being held invalid.

- Set out the basis line by line. Each one should be capable of being checked against a valuation, an instruction, a signed record or an invoice.

- Serve the notice by the method the contract requires and keep proof of the date it was sent and received. The burden of showing a notice was served in time falls on the party who gave it.

- A payment notice given late is not a payment notice. Where the payer gives none in time, the payee’s application becomes the notified sum and is payable in full by the final date for payment unless a valid pay less notice follows.

- Retention deducted under the contract is not a set-off and needs no pay less notice. Any other deduction does, so keep the two apart on the basis of calculation.

- Assessment dates fall at the interval stated in Contract Data part one, commonly monthly (clause 50.1).

- The Project Manager certifies payment within one week of each assessment date, showing how the amount was assessed (clause 51.1).

- Payment is made within three weeks of the assessment date, unless a different period is stated in Contract Data (clause 51.2).

- Secondary Option Y(UK)2 makes the contract Construction Act compliant: the Project Manager’s certificate is the payment notice, and the contract sets a due date and a final date for payment from the assessment date.

- Under the standard Y(UK)2 the due date is 7 days after the assessment date, the final date for payment is 14 days after the due date, and a notice of intention to pay less is given not later than 7 days before the final date for payment. NEC’s October 2020 guidance on Y(UK)2 describes an amended secondary Option, so check which edition your contract incorporates and what Contract Data says.

## SOURCES

NEC4 ECC clauses 50.1, 51.1 and 51.2 and secondary Option Y(UK)2, as summarised by HKA, "How to get your NEC4 ECC pay less notice right under Y(UK)2" — hka.com

Housing Grants, Construction and Regeneration Act 1996, Part II, ss.109–111 (as amended by the Local Democracy, Economic Development and Construction Act 2009) — legislation.gov.uk/ukpga/1996/53/part/II

This template is general information, not legal advice. Contract particulars routinely amend the default timings — always check your own contract.

Version 2.0 · Last reviewed 2 September 2026