PAYMENT NOTICE

Scheme default

Issued under the Scheme for Construction Contracts (England and Wales) Regulations 1998, Part II. A notice under section 110A of the Housing Grants, Construction and Regeneration Act 1996.

| Reference | PN-7 / KMD/2025/014 |
| --- | --- |
| Date | 27/01/2026 |
| Version | Worked example |

## 1. CONTRACT AND PAYMENT CYCLE

| Project | Kingsmead Depot Refurbishment |
| --- | --- |
| Contract reference | KMD/2025/014 |
| Payer (issuing this notice) | Northfield Civil Engineering Ltd |
| Payee | Ashdown Groundworks Ltd |
| Payment cycle / valuation number | 7 |
| Interim valuation or assessment date | 15/01/2026 |
| Payment due date | 22/01/2026 |
| Final date for payment | 08/02/2026 |

## 2. NOTICE DETAILS

| Application or assessment being responded to | Application 7, submitted 15/01/2026 |
| --- | --- |
| Sum applied for, excluding VAT | £32,277.50 |
| Sum the payer considers due at the payment due date, excluding VAT | £32,277.50 |
| VAT at 20% | £6,455.50 |
| Total payable, including VAT | £38,733.00 |
| Date of this notice | 27/01/2026 |

## 3. BASIS OF CALCULATION

| Element | Description and reference | Amount (£) |
| --- | --- | --- |
| Measured work | Valuation 7, measured work sheet | £87,400.00 |
| Variations | VO-004 to VO-006, agreed and instructed | £12,500.00 |
| Dayworks | DW-011 and DW-012, signed on site | £3,250.00 |
| Materials on site | Kerb and sub-base stock, vested and insured | £4,200.00 |
| Preliminaries | Welfare, supervision and plant standing earned to date | £8,400.00 |
| Gross valuation to date | Sum of the five lines above | £115,750.00 |
| Less: retention at 3% | Contract particulars | -£3,472.50 |
| Less: previously certified | Valuations 1 to 6 | -£80,000.00 |
| Sum considered due, excluding VAT | Net of retention and earlier certificates | £32,277.50 |
| VAT at 20% | Standard rate — no domestic reverse charge on this supply | £6,455.50 |
| Total payable, including VAT | The figure to pay by the final date | £38,733.00 |

## 4. ISSUE AND SERVICE

Issued by (name and position):  H. Okafor, Quantity Surveyor

Method of service:  Email, as the contract particulars require

Date and time served:  27/01/2026 at 10:14

## 5. SIGN-OFF

| Party | Name (print) | Position | Signature | Date |
| --- | --- | --- | --- | --- |
| Payer | H. Okafor | Quantity Surveyor |  | 27/01/2026 |

## 6. HOW TO USE THIS NOTICE

Reference, not part of the notice itself.

- This notice must state the sum the payer considers to be or to have been due at the payment due date, and the basis on which that sum is calculated. A notice that states a figure without a basis is at risk of being held invalid.

- Set out the basis line by line. Each one should be capable of being checked against a valuation, an instruction, a signed record or an invoice.

- Serve the notice by the method the contract requires and keep proof of the date it was sent and received. The burden of showing a notice was served in time falls on the party who gave it.

- A payment notice given late is not a payment notice. Where the payer gives none in time, the payee’s application becomes the notified sum and is payable in full by the final date for payment unless a valid pay less notice follows.

- Retention deducted under the contract is not a set-off and needs no pay less notice. Any other deduction does, so keep the two apart on the basis of calculation.

- Use this version where the contract has no compliant payment mechanism of its own, so the Scheme supplies the missing terms.

- Payment becomes due on the later of 7 days after the end of the relevant period and the making of the payee’s claim (paragraph 4).

- The final date for payment is 17 days from the date payment becomes due (paragraph 8).

- The payer must give a payment notice not later than 5 days after the payment due date (paragraph 9).

- A pay less notice must be given not later than 7 days before the final date for payment (paragraph 10).

- The Scheme fills gaps clause by clause. Where the contract has a compliant mechanism for one of these, that clause stands and only the missing ones are supplied.

## SOURCES

Scheme for Construction Contracts (England and Wales) Regulations 1998, Schedule Part II, paragraphs 4, 8, 9 and 10 — legislation.gov.uk/uksi/1998/649/schedule/part/II

Housing Grants, Construction and Regeneration Act 1996, Part II, ss.109–111 (as amended by the Local Democracy, Economic Development and Construction Act 2009) — legislation.gov.uk/ukpga/1996/53/part/II

This template is general information, not legal advice. Contract particulars routinely amend the default timings — always check your own contract.

Version 2.0 · Last reviewed 2 September 2026