## Payment Schedule
PAYMENT SCHEDULE — WHOLE CONTRACT
Every payment cycle to the end of the contract, with the four statutory dates calculated for each · complete the yellow cells only
Payer (employer / main contractor) |  |  |  | Contract form |  | JCT SBC/Q 2016
Payee |  |  |  | Valuation / assessment date
Project |  |  |  | Payment due date
Site address |  |  |  | Payer's notice by
Contract reference |  |  |  | Pay less notice deadline
Application / valuation number |  |  |  | Final date for payment
Claim date — Scheme only
Cycle no. | Period end / valuation date | Application submitted | Due date | Payer’s notice due | Pay less notice deadline | Final date for payment | Notified sum (£) | Paid (£) | Shortfall (£) | Status | Notes
Payment Schedule — total

## How to use
Payment schedule — how to use this workbook
FIELD BY FIELD
Fill this in once, at contract award, for every payment cycle to the end of the contract. The point is that the deadlines exist on a calendar before the first application, not after the first one goes wrong.
Contract form: pick it once in the header. Every row then calculates its own due date, payer’s notice date, pay less deadline and final date for payment from the period end date you enter.
Period end / valuation date: the Interim Valuation Date under JCT, the assessment date under NEC4, or the end of the relevant period under the Scheme. Take the dates from your contract particulars.
Application submitted: the date you actually sent it, and under the Scheme the payee’s claim. The due date column reads it: on the Scheme the due date is the later of seven days after the period end and the date of the claim, so a late application moves the whole cycle.
Notified sum: what became payable for that cycle — your application where no compliant payment notice was given, or the sum in the payer’s notice where one was.
Shortfall: the adjudication evidence. A notified sum not paid in full by the final date, with no pay less notice, is the simplest claim there is.
The final date column turns amber as it approaches, so the row that needs chasing this week is visible without reading the whole schedule.
Statutory interest on a late commercial debt runs at 8% above the Bank of England base rate, plus fixed compensation of £40, £70 or £100 depending on the size of the debt.
STATUTORY AND STANDARD-FORM TIMINGS
Day counts are calendar days. The workbook computes the four dates in the header from the contract form you pick and the valuation date you enter.
Contract form | Due date | Payer's notice | Final date | Pay less by
JCT SBC/Q 2016 — JCT Standard Building Contract with Quantities 2016 (SBC/Q) | +7 days | +5 days | +14 days | -5 days
JCT DB 2016 — JCT Design and Build 2016 (DB) | +7 days | +5 days | +14 days | -5 days
NEC4 ECC — NEC4 Engineering and Construction Contract | +7 days | +0 days | +14 days | -7 days
Scheme default — Scheme for Construction Contracts (default) | +7 days | +5 days | +17 days | -7 days
Due date counts from the valuation, assessment or period-end date. The payer’s notice and the final date count from the due date. The pay less deadline counts back from the final date.
SOURCES
Housing Grants, Construction and Regeneration Act 1996, Part II, ss.109–111 (as amended by the Local Democracy, Economic Development and Construction Act 2009) — legislation.gov.uk/ukpga/1996/53/part/II
Scheme for Construction Contracts (England and Wales) Regulations 1998, Schedule Part II, paragraphs 4, 8, 9 and 10 — legislation.gov.uk/uksi/1998/649/schedule/part/II
JCT, "JCT explains: interim payments" (SBC/Q 2016 clauses 4.9 and 4.11) — corporate.jctltd.co.uk/jct-explains-interim-payments/
NEC4 ECC clauses 50.1, 51.1 and 51.2 and secondary Option Y(UK)2, as summarised by HKA, "How to get your NEC4 ECC pay less notice right under Y(UK)2" — hka.com
Late Payment of Commercial Debts (Interest) Act 1998, s.5A, and gov.uk "Late commercial payments: charging interest and debt recovery" — legislation.gov.uk/ukpga/1998/20/section/5A
This template is general information, not legal advice. Contract particulars routinely amend the default timings — always check your own contract.
Version 2.0 · Last reviewed 2 September 2026 · sitesamurai.co.uk/resources/get-paid-on-time