## Retention Ledger
RETENTION STATEMENT
How much has been withheld, on what basis, and what has been released · attach it to every release request
Payer (employer / main contractor) |  | Northfield Civil Engineering Ltd |  | Contract form |  | JCT SBC/Q 2016
Payee |  | Ashdown Groundworks Ltd |  | Valuation / assessment date |  | 2026-01-15
Project |  | Kingsmead Depot Refurbishment |  | Payment due date
Site address |  | Kingsmead Depot, Northfield Road, Kingsmead KM4 7QT |  | Payer's notice by
Contract reference |  | KMD/2025/014 |  | Pay less notice deadline
Final date for payment
|  |  |  | Claim date — Scheme only |  | 2026-01-15
Valuation no. | Certificate date | Gross valuation to date (£) | Retention % | Retention held this cycle (£) | Cumulative held (£) | First moiety released (£) | Second moiety released (£) | Balance held (£) | Notes
1 | 2025-07-22 | 6000 | 3% |  |  | 0 | 0
2 | 2025-08-22 | 15500 | 3% |  |  | 0 | 0
3 | 2025-09-21 | 29500 | 3% |  |  | 0 | 0
4 | 2025-10-22 | 47000 | 3% |  |  | 0 | 0
5 | 2025-11-21 | 62200 | 3% |  |  | 0 | 0 |  | Certified below the valuation
6 | 2025-12-22 | 79200 | 3% |  |  | 0 | 0
7 | 2026-01-27 | 115750 | 3% |  |  | 0 | 0 |  | Application 7 certified
| 2026-03-20 |  |  |  |  | 1736.25 | 0 |  | Due 27/02/2026 on practical completion, paid on request RR-01
Retention Ledger — total
RETENTION POSITION
Total retention held to date |  |  |  | Sum of the ledger above
First moiety percentage |  | 50% |  | Usually half, released on practical completion
First moiety due on release |  |  |  | Released on practical completion
Released to date |  |  |  | First and second moiety columns of the ledger
Balance still held |  |  |  | What the release request is for
BASIS
Retention is deducted under the contract particulars named above. It is a contractual deduction rather than a set-off, so it does not require a pay less notice — but a certified release that is then not paid in full by the final date for payment is an ordinary notified-sum claim.
Party |  | Name (print) |  | Position |  | Signature |  | Date
Prepared by
Agreed by

## Release Tracker
RELEASE TRACKER
The two contractual release triggers and whether they have been asked for
Payer (employer / main contractor) |  |  | Contract form
Payee |  |  | Valuation / assessment date
Project |  |  | Payment due date
Site address |  |  | Payer's notice by
Contract reference |  |  | Pay less notice deadline
Final date for payment
Claim date — Scheme only
Project | Retention held (£) | Practical completion | First release due | First release amount (£) | Rectification period ends | Certificate of making good | Second release due | Second release amount (£) | Status
Kingsmead Depot Refurbishment | 3472.5 | 2026-02-27 | 2026-02-27 | 1736.25 | 2027-02-27 |  | 2027-02-27 | 1736.25 | First moiety released
Release Tracker — total

## How to use
Retention statement — how to use this workbook
FIELD BY FIELD
A retention statement shows how much has been withheld across the contract, on what basis, and what has been released. It is the document you attach to a release request so the payer does not have to reconstruct the arithmetic.
Retention Ledger: one row per certificate. Enter the gross valuation to date — cumulative, not the payment — and the retention percentage. The cycle deduction is calculated on the increase since the row above, so the cumulative held is always the retention percentage of the gross valued.
There is no statutory retention scheme in the UK and no statutory release date. Retention is entirely contractual, so every trigger date on the Release Tracker comes from your contract rather than from legislation.
JCT sets a default retention percentage of 3%, very commonly amended upward to 5%. Half is typically released on practical completion and the balance on the certificate of making good at the end of the rectification period.
Since the 2011 amendments to the Construction Act, a subcontract cannot make the release of your retention conditional on an event under a different contract, such as the main contractor being paid its own retention upstream.
Retention release is a payment under the contract. It goes through the same payment notice and pay less notice machinery, so a release that is certified and then not paid is an ordinary notified-sum claim.
The release dates on the tracker turn amber as they approach. Diarise both at contract award: retention is the money most often lost simply because nobody asked for it.
STATUTORY AND STANDARD-FORM TIMINGS
Day counts are calendar days. The workbook computes the four dates in the header from the contract form you pick and the valuation date you enter.
Contract form | Due date | Payer's notice | Final date | Pay less by
JCT SBC/Q 2016 — JCT Standard Building Contract with Quantities 2016 (SBC/Q) | +7 days | +5 days | +14 days | -5 days
JCT DB 2016 — JCT Design and Build 2016 (DB) | +7 days | +5 days | +14 days | -5 days
NEC4 ECC — NEC4 Engineering and Construction Contract | +7 days | +0 days | +14 days | -7 days
Scheme default — Scheme for Construction Contracts (default) | +7 days | +5 days | +17 days | -7 days
Due date counts from the valuation, assessment or period-end date. The payer’s notice and the final date count from the due date. The pay less deadline counts back from the final date.
SOURCES
BESA, "Retentions and security" and Designing Buildings, "Retention" — thebesa.com/payments/retentions-security
Housing Grants, Construction and Regeneration Act 1996, Part II, ss.109–111 (as amended by the Local Democracy, Economic Development and Construction Act 2009) — legislation.gov.uk/ukpga/1996/53/part/II
JCT, "JCT explains: interim payments" (SBC/Q 2016 clauses 4.9 and 4.11) — corporate.jctltd.co.uk/jct-explains-interim-payments/
This template is general information, not legal advice. Contract particulars routinely amend the default timings — always check your own contract.
Version 2.0 · Last reviewed 2 September 2026 · sitesamurai.co.uk/resources/get-paid-on-time