## Variation Register
VARIATION ORDER AND CHANGE REGISTER
Every instructed change, what it was worth and which valuation it was paid in · complete the yellow cells only
Payer (employer / main contractor) |  |  |  | Contract form |  | JCT SBC/Q 2016
Payee |  |  |  | Valuation / assessment date
Project |  |  |  | Payment due date
Site address |  |  |  | Payer's notice by
Contract reference |  |  |  | Pay less notice deadline
Application / valuation number |  |  |  | Final date for payment
Claim date — Scheme only
Variation no. | Instruction ref | Date instructed | Description of the change | Instruction type | Status | Value (£) | Included in valuation no. | Notes
Agreed, carry to the application — total
Quoted, awaiting agreement — total
Notified, not yet quoted — total
Disputed or rejected — total

## Compensation Events
COMPENSATION EVENTS
NEC4 events, notified and assessed from a quotation
Payer (employer / main contractor) |  |  |  |  | Contract form
Payee |  |  |  |  | Valuation / assessment date
Project |  |  |  |  | Payment due date
Site address |  |  |  |  | Payer's notice by
Contract reference |  |  |  |  | Pay less notice deadline
Application / valuation number |  |  |  |  | Final date for payment
Claim date — Scheme only
CE no. | Date of event | Date notified | Notified by | Clause 60.1 sub-clause relied on | Description | Quotation submitted | Quotation (£) | Assessed (£) | Change to Completion Date (days) | Status
Assessed, carry to the application — total
Quoted, awaiting assessment — total
Notified, not yet quoted — total
Not a compensation event — total

## How to use
Variations and compensation events — how to use this workbook
FIELD BY FIELD
Use the Variation Register where the contract calls the change a variation and values it after the fact. Use the Compensation Events sheet where the contract calls it a compensation event and prices it prospectively from a quotation.
The two mechanisms are not interchangeable. A JCT variation is usually valued against the contract rates once the work is done. An NEC4 compensation event is assessed from a forecast of the effect on Defined Cost, and the assessment is not revisited because the forecast turned out wrong.
Instruction type: log the instruction before you log the price. The most expensive variations are the ones done on a verbal instruction nobody confirmed in writing, which is what this column exists to make visible while you can still fix it.
Value and Status: the totals under the grid are split by status, so an agreed variation is never added to one that is only priced. Only the first total — agreed — is money you can carry into a payment application; the rest is the open negotiation on the job.
Included in valuation no.: an agreed variation nobody applied for is money you have already earned and not asked for. This column is the check against that.
NEC4 puts time limits on notifying a compensation event and on replying to a quotation. Track the dates and read your own clause 61 and 62 periods, which Contract Data can change.
A variation that is agreed but unpaid is still subject to the payment notice machinery. It has no separate payment route of its own.
STATUTORY AND STANDARD-FORM TIMINGS
Day counts are calendar days. The workbook computes the four dates in the header from the contract form you pick and the valuation date you enter.
Contract form | Due date | Payer's notice | Final date | Pay less by
JCT SBC/Q 2016 — JCT Standard Building Contract with Quantities 2016 (SBC/Q) | +7 days | +5 days | +14 days | -5 days
JCT DB 2016 — JCT Design and Build 2016 (DB) | +7 days | +5 days | +14 days | -5 days
NEC4 ECC — NEC4 Engineering and Construction Contract | +7 days | +0 days | +14 days | -7 days
Scheme default — Scheme for Construction Contracts (default) | +7 days | +5 days | +17 days | -7 days
Due date counts from the valuation, assessment or period-end date. The payer’s notice and the final date count from the due date. The pay less deadline counts back from the final date.
SOURCES
Housing Grants, Construction and Regeneration Act 1996, Part II, ss.109–111 (as amended by the Local Democracy, Economic Development and Construction Act 2009) — legislation.gov.uk/ukpga/1996/53/part/II
JCT, "JCT explains: interim payments" (SBC/Q 2016 clauses 4.9 and 4.11) — corporate.jctltd.co.uk/jct-explains-interim-payments/
NEC4 ECC clauses 50.1, 51.1 and 51.2 and secondary Option Y(UK)2, as summarised by HKA, "How to get your NEC4 ECC pay less notice right under Y(UK)2" — hka.com
This template is general information, not legal advice. Contract particulars routinely amend the default timings — always check your own contract.
Version 2.0 · Last reviewed 2 September 2026 · sitesamurai.co.uk/resources/get-paid-on-time